SCHEDULE "B"

ATTACHMENT II

CRITICAL MILESTONE DATES

1. Milestone Dates

The following constitutes the Critical Milestone Dates, as referenced in Paragraph 1.5 of Schedule “B”.

|  | Milestone Events | No. of Calendar Days After the Effective Date of the Contract |
| --- | --- | --- |
|  | Construction and Procurement |  |
| 1.01 | Site mobilization complete, including all temporary construction facilities for start of construction | 60 |
| 1.02 | Complete site preparation | 100 |
| 1.03 | Site Delivery of all Major Material | 180 |
| 1.04 | Site Delivery of all other Material | 250 |
| 1.05 | Complete Pipeline installation | 360 |
| 1.06 | Complete all civil & structural works | 460 |
| 1.07 | Complete all mechanical & all Tie-Ins works | 460 |
| 1.08 | Complete Cathodic Protection System | 400 |
| 1.09 | Complete all electrical & instrumentation work | 500 |
| 1.10 | Complete all equipment installation including cyclone separator work | 500 |
| 1.11 | Demolition of existing piping, mechanical and electrical works | 550 |
| 1.12 | Complete all facilities Pre-commissioning | 600 |
| 1.13 | Final Mechanical Completion | 650 |
| 1.14 | Provide As built drawings, remaining project record books and other required documents | 700 |
| 1.15 | Project Completion and Demobilization | 750 |

2.0 DEFINITION OF CRITICAL MILESTONE DATES

CONTRACTOR shall complete all required activities for the milestones, including the following:

2.01 Site mobilization complete, including all temporary construction facilities for start of construction

Mobilization of appropriate resources and personnel to the site has been completed, and all construction camp and project support buildings facilities are ready.

2.02 Complete site preparation

CONTRACTOR shall have completed all site preparation, earthwork grading and compaction, identification of existing underground utilities and fencing to allow follow-on activities such as foundation construction, and underground services, to commence.

2.03 Site Delivery of all major Material

All major Material shall be delivered to the site by the Milestone Date.

2.04 Site Delivery of all other Material

All other Material shall be delivered to the site by the Milestone Date.

2.05 Complete Pipeline installation

CONTRACTOR shall complete all pipeline installation activities required for the project.

2.06 Complete all civil & structural works

CONTRACTOR shall complete all civil & structural works activities required for the project.

2.07 Complete all mechanical & all Tie-Ins works

CONTRACTOR shall complete all mechanical & Tie-Ins works activities required for the project.

2.08 Complete Cathodic Protection System

CONTRACTOR shall complete all Cathodic Protection System works activities required for the project.

2.09 Complete all electrical & instrumentation work

CONTRACTOR shall complete all electrical & instrumentation work

activities required for the project.

2.10 Complete all equipment installation including cyclone separator work

CONTRACTOR shall complete all equipment installation including cyclone separator work activities required for the project.

2.11 Complete demolition of existing piping, mechanical and electrical works

CONTRACTOR shall complete all demolition of existing piping, mechanical and electrical works activities required for the project.

2.12 Complete all facilities Pre-commissioning

CONTRACTOR shall complete all facilities Pre-commissioning works activities required for the project.

2.13 Final Mechanical Completion

The final and all partial Mechanical Completion certificates have been signed by all required SAUDI ARAMCO Departments.

2.14 Project As built drawings, remaining Project record books and other required documents

Submit all as built drawings and upload it in IPLANT System, as well as provide the project record books and other required documents referenced in the Job Specification before Final Mechanical Completion to support the Commissioning activities.

2.15 Project Completion and Demobilization

The FACILITIES are commissioned by SAUDI ARAMCO with Commissioning assistance provided by CONTRACTOR The FACILITY is “On-stream”, and all performance items have been corrected, all demolition completed and the temporary facilities have been removed.

END OF ATTACHMENT II TO SCHEDULE “B”